## Eggs
| #Tasks: 14 | #Top: 3 | [10 empty] | computed start | computed end | computed Cost
Task: | 100 | Text: | Prepare Fry | Mama: | 0 | Start: | 1 | End: | 12 | Cost: | 60 |  | 1 | 12 | 60
Task: | 101 | Text: | Turn on burner (low) | Mama: | 100 | Start: | 1 | End: | 1 | Cost: | 10
Task: | 102 | Text: | Break eggs and pour into fry | Mama: | 100 | Start: | 2 | End: | 4 | Cost: | 10
Task: | 103 | Text: | Steer mixture to avoid sticking | Mama: | 100 | Start: | 5 | End: | 10 | Cost: | 10
Task: | 104 | Text: | Throw yellow cheese into fry | Mama: | 100 | Start: | 6 | End: | 12 | Cost: | 10
Task: | 105 | Text: | Salt, pepper | Mama: | 100 | Start: | 5 | End: | 5 | Cost: | 10
Task: | 106 | Text: | Turn burner off | Mama: | 100 | Start: | 12 | End: | 12 | Cost: | 10
Task: | 200 | Text: | Prepare the bread | Mama: | 0 | Start: | 10 | End: | 12 | Cost: | 20 |  | 10 | 12 | 20
Task: | 201 | Text: | Heat bread in toaster | Mama: | 200 | Start: | 10 | End: | 12 | Cost: | 10
Task: | 202 | Text: | Little bit of salt, galric spice to bread | Mama: | 200 | Start: | 12 | End: | 12 | Cost: | 10
Task: | 300 | Text: | Serve eggs | Mama: | 0 | Start: | 13 | End: | 20 | Cost: | 30 |  | 13 | 20 | 30
Task: | 301 | Text: | Put bread in plate | Mama: | 300 | Start: | 13 | End: | 13 | Cost: | 10
Task: | 302 | Text: | Put eggs on bread | Mama: | 300 | Start: | 14 | End: | 14 | Cost: | 10
Task: | 304 | Text: | Wash fry | Mama: | 300 | Start: | 15 | End: | 20 | Cost: | 10
14 lines parsed | [11 empty] | Project | 1 | 20 | 110
Prj: ./src/main/resources/input/Eggs.tsv